# Heart of Ruin – Modified MoSCoW Analysis

This document outlines the prioritised features for the Heart of Ruin vertical slice. It includes both Vertical Slice (VS) and Full Game (FG) priorities, estimated development time in weeks, and a placeholder for skills showcase entries.

DM – David Mulgrew		CS- Callum Streets		SH – Steven Holmes

| Priority VS | Priority FG | Feature ID | Related ID | Feature Name | Description | Estimate Time (wks) | Skill Showcase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M | M | FA-01 | FP-03 | Enemy Spawner | Procedurally populate rooms with enemies. | 2 |  |
| M | M | FA-02 |  | Enemy Behaviour AI | Basic AI with patrol, chase, and attack. | 3 | CS |
| M | M | FA-04 | FG-02 | Damage System | Handles damage, resistances, and mitigation. | 2 | CS |
| M | M | FG-01 | FS-01 | Player Character Control | Player movement, dash/dodge, and attack input. | 2 |  |
| M | M | FG-02 | FA-04 | Combat System | Combat loop, hit detection, and feedback. | 2 | CS |
| M | M | FG-04 | FP-01 | Player Death & Run Reset | Run reset and persistence between runs. | 1 |  |
| M | M | FG-06 | FA-03 | Boss Encounter System | Boss spawn, activation, and control system. | 2 |  |
| M | M | FG-07 | FG-06 | Tension Meter | Tracks dungeon time and triggers boss breach. | 1 |  |
| M | M | FG-09 |  | Resource Management | Unified health/mana/stamina system. | 1 |  |
| M | M | FI-02 | FI-01 | Weapon Framework | Base weapon class for melee/ranged/magic. | 2 | CS |
| M | M | FP-01 | FS-02 | Safe Point Hub | Hub for upgrades, vendors, and rest points. | 3 |  |
| M | M | FS-01 |  | Game Manager | Controls core game states and transitions. | 2 |  |
| M | M | FS-03 | FP-02 | Save/Load System | Handles save data and upgrades. | 3 |  |
| M | M | FS-04 | FG-08 | Event Messaging System | Broadcast gameplay events. | 1 |  |
| M | M | FU-01 | FG-09 | HUD | Display health, mana, and tension. | 1 |  |
| S | M | FU-02 | FI-01 | Inventory UI | Equip and view items. | 1 |  |
| S | M | FA-03 | FG-06 | Boss AI | Phase-based boss with adaptive behaviour. | 2 | CS |
| S | M | FG-03 |  | Action-Based Levelling | Stat gain/loss based on usage. | 1 | DM |
| S | S | FG-05 | FA-04 | Buffs and Curses | Temporary modifiers triggered by actions or RNG. | 1 |  |
| S | M | FI-01 | FU-02 | Inventory System | Manage weapons, consumables, and relics. | 2 |  |
| S | M | FI-04 | FP-03 | Loot Generation | Random loot tables with rarity weighting. | 2 |  |
| S | M | FM-01 |  | Co-Op Party Play | Online co-op for 4–5 players. | 2 | DM |
| S | M | FO-01 |  | Ability Unlock System | Permanent/run-based ability unlocks. | 2 |  |
| S | M | FO-02 |  | Curse/Buff Visual Feedback | Shaders or VFX for buffs and curses. | 2 | CS, DS |
| S | M | FP-02 | FS-03 | Permanent Upgrades | Persistent unlock system. | 2 |  |
| S | M | FP-04 | FP-03 | Biome Definition | Biome configuration for visuals and modifiers. | 2 |  |
| S | M | FP-05 | FG-06 | Floor Progression | Sequential floors and boss checks. | 2 |  |
| S | S | FP-06 | FP-03 | Editor-time Curated Procedural Generator | Curated dungeons generated pre-runtime. | 2 | SH |
| S | M | FS-02 |  | Scene Management | Load/unload scenes additively. | 3 | DM,CS |
| S | M | FS-05 |  | Audio Manager | Handles BGM and SFX. | 2 |  |
| S | M | FS-06 | FP-03 | Procedural Seed Manager | Ensures repeatable procedural runs. | 1 |  |
| S | M | FS-07 | FU-05 | Options Manager | Save/load player settings. | 1 |  |
| S | M | FS-09 | FS-07 | Accessibility Manager | Handle accessibility features. | 1 | DM |
| S | S | FT-04 |  | Test Logging | Record playtest data. | 1 |  |
| S | M | FT-05 |  | Remote Debugging Console | Stream console output remotely. | 0 | DM |
| S | S | FU-03 | FP-01 | Shop UI | Vendor interface for purchases. | 2 |  |
| S | M | FU-05 | FS-07 | Pause & Settings Menu | Settings for controls and volume. | 1 |  |
| S | S | FU-07 | FS-07 | Options UI | Player options configuration. | 1 |  |
| S | C | FG-08 | FS-04 | Event System | Framework for random dungeon events. | 2 |  |
| S | M | FU-08 |  | Minimap | Generated mini-map | 2 |  |
| C | S | FI-03 | FU-06 | Crafting Prototype | Basic crafting to modify weapons. | 2 | DM |
| C | S | FM-02 |  | Death Echoes | Show remnants of fallen players. | 1 | DM |
| C | S | FM-03 |  | Flare System | Trigger signal visible to nearby players. | 2 | DM |
| C | S | FM-04 | FM-03 | Pseudo Party | Temporary auto-parties formed by flares. | 2 | DM |
| C | S | FO-03 |  | Procedural Narrative Hooks | Lore fragments and story generation. | 2 |  |
| C | M | FP-03 | FS-06 | Full Runtime Procedural Dungeon Generator | Runtime procedural dungeon generation. | 12 | SH, DM |
| C | S | FS-08 | FS-07 | Graphics Manager | Manage graphics settings. | 1 | DM |
| C | S | FT-01 |  | Developer Console | In-game console for debug testing. | 1 |  |
| C | S | FT-02 |  | Debug Overlay | Displays runtime stats and metrics. | 1 |  |
| C | S | FT-03 |  | Procedural Debug Tools | Visualise dungeon generation. | 2 |  |
| C | S | FT-06 |  | Object Pooling System | Dynamic pool manager to extend unity pool system | 1 | DM |
| C | S | FU-04 |  | Dialogue UI | NPC dialogue system. | 2 |  |
| C | S | FU-06 | FI-03 | Crafting UI | Basic interface for crafting. | 1 | DM |
| W | S | FM-05 |  | Leaderboards | Track and display player stats and scores. | 2 |  |
| W | C | FM-06 |  | PVP | Competitive mode with player battles. | 6 | DM |
| W | C | FM-07 |  | World Bosses | Large event bosses for multiple players. | 8 | DM |
| W | C | FM-08 |  | RAIDs | Multi-party dungeons or bosses. | 10 | DM |